## Sheet1
Issue # | Name | Assigned | Milestone | Milestone Due Date
22 | Initial Raspberry Pi Setup | Felipe | All Sensors Tested | 2017-02-13
23 | Test GPS Module | Felipe | All Sensors Tested | 2017-02-13
24 | Test Xbee & Adapter Board | Genesis | All Sensors Tested | 2017-02-13
42 | Configure Controller Database | Garvin | Back End Setup Complete | 2017-02-13
43 | Configure Server Database | Felipe | Back End Setup Complete | 2017-02-13
27 | Magnetic Field Sensor - Practical Testing Prototype | Anthony | CAD Designs Completed | 2017-02-27
28 | Design PCBs | Genesis | CAD Designs Completed | 2017-02-27
29 | Wireless Communications Circuit Design | Genesis | CAD Designs Completed | 2017-02-27
30 | Perform Circuit Simulations | Genesis | CAD Designs Completed | 2017-02-27
31 | Design Substation Diagrams | Genesis | Mobile App Front End Complete | 2017-02-27
33 | Design auto Dimming Circuit for LEDs | Genesis | CAD Designs Completed | 2017-02-27
35 | Mobile App UI Mockup | Garvin | Mobile App Front End Complete | 2017-02-27
36 | Model Case Outer Shell | Anthony | CAD Designs Completed | 2017-02-27
37 | Model Component Support Case | Felipe | CAD Designs Completed | 2017-02-27
47 | Program Mobile App Front End | Garvin | Mobile App Front End Complete | 2017-02-27
48 | Program Mobile App Back End | Garvin | Mobile App Front End Complete | 2017-02-27
32 | Implement Auto Dimming Circuit for LEDs | Anthony | PCBs Complete | 2017-03-06
34 | Hook up Charging Circuit to Raspberry Pi | Anthony | PCBs Complete | 2017-03-06
50 | Replace Headers on Raspberry Pi | Anthony | PCBs Complete | 2017-03-06
53 | Mobile Back End - Remote DB Interface | Garvin | Mobile App Back End Complete | 2017-03-13
54 | Mobile Back End - Bluetooth Connection | Garvin | Mobile App Back End Complete | 2017-03-13
55 | Mobile Back End - Local DB Interface | Garvin | Mobile App Back End Complete | 2017-03-13
25 | Test Components Power Draw | Genesis | Hardware Fitting Complete | 2017-03-20
26 | Solder Headers on Controller | Anthony | Hardware Fitting Complete | 2017-03-20
44 | Route Earbuds and Microphone through Hardhat | Felipe | Hardware Fitting Complete | 2017-03-20
45 | Mount LEDs on Hardhat | Felipe | Hardware Fitting Complete | 2017-03-20
49 | Remove USA and Ethernet Ports | Anthony | Hardware Fitting Complete | 2017-03-20
51 | Hardhat Modifications | Felipe | Hardware Fitting Complete | 2017-03-20
52 | Component Wire Touring | Felipe | Hardware Fitting Complete | 2017-03-20
38 | Write Code to Read GPS Coordinates | Felipe | Software Development Freeze | 2017-04-03
39 | Write Code to Read Magnetic Field Sensor | Genesis | Software Development Freeze | 2017-04-03
40 | Write Code to Initate Phone Call | Genesis | Software Development Freeze | 2017-04-03
41 | Write Code to Perform Data Transfer over GSM Network | Genesis | Software Development Freeze | 2017-04-03